## Gap Register
ID | Layer | Gap | Production behavior | Current behavior | Missing rule / logic | Impact | Severity | Recommended fix direction | Step | Status
G1 | A - Prompt authority | Per-turn mandate removed | prompt.ts:427 "Use at the end of every Flight Agent turn"; :655 "Before final response, always update Flight suggested questions"; :171 stop rule "Perform only the mandatory final suggested-questions update, then respond". | prompt.ts:137 "This is optional, best-effort enrichment"; :71 "Optional suggestion enrichment may run once"; agent.ts:229 repeats "Suggested questions are optional". | Any unconditional statement that the turn is not finished until the tool has run. | 43% call rate across 201 recorded turns; 0% on read-only, prediction and no-tool turns. | High | Replace the optional framing in all three live locations with a required-final-step rule. | Step 3 | Open
G2 | A - Prompt authority | Approved tool-chain table absent | prompt.ts:660-676 lists 15 chains, every one terminating in this tool, including "update_flight_suggested_questions alone for missing-info, clarification, source-option, or no-action responses". | FLIGHT_PROMPT contains no chain table at all. | Per-request-class sequencing that names the tool as the terminal step. | The three 0% measured rows map one-to-one onto the missing chains (contract read, prediction, no-tool). | High | Add a compact chain list ending in the tool; the standalone clarification case matters most (0/12 turns today). | Step 3 | Open
G3 | A - Prompt authority | Pre-response checklist gone | prompt.ts:908 "Did I call update_flight_suggested_questions as the final tool call and avoid mentioning its result to the user?" | No checklist of any kind in the live prompt. | A self-verification pass before the final output is emitted. | No second chance for the model to notice the omission. | Medium | One checklist line in the "Final response and stopping" section. | Step 3 | Open
G4 | A - Prompt authority | A clause actively instructs the model to drop it | Turn budget was never traded against this tool. | prompt.ts:143 "Search/filter/contract success outranks suggestion enrichment. Prioritize completing structured feedback within the turn budget over optional work." | Nothing - this is an added counter-incentive rather than an omission. | With maxTurns: 10 (config.ts:88) this is the first thing dropped under pressure. | High | Keep "never let it discard a successful result"; delete the optional-work / budget trade-off framing. | Step 3 | Open
G5 | A - Prompt authority | Manager-mode instructions de-escalate it | The agent ended its turn in free text, so "final tool call before your final text response" was a coherent instruction. | FlightManagerAgent sets outputType: flightManagerOutputSchema (agent.ts:250) so the turn ends by emitting JSON; manager-output.ts:38 says "Optional suggested-question work never changes a successful core outcome." | An ordering rule: tool call first, structured output second. | Manager-path call rates of 43% (manager-flight-*) and 35% (manager-realistic-*). | High | State the ordering in FLIGHT_MANAGER_INSTRUCTIONS and drop the de-escalation sentence. Do NOT add a schema field - the consumer reads shared context, not Manager feedback. | Step 3 | Open
G6 | B - Tool definition | Tool description contradicts any mandate | A "Required behavior" block: call it as the final tool call before the final text response. | suggested-questions-tool.ts:84 "Best-effort enrichment after the user’s core Flight request is complete..." | Required/terminal framing in the text the model receives alongside the tool schema. | The description ships in the same payload as the prompt and will undercut G1. | High | Mirror the trip-planner sibling: "Call only after context capture and all planning tools, as the final tool call." (trip-planner/tools/context-tools.ts:205-206) | Step 2 | Open
G7 | B - Tool definition | Schema admits a payload that can only fail | "Exactly 3" was prose only, same as here. | suggested-questions-tool.ts:16-23 uses .array(z.string().min(1)).max(3) with no .min(3). The provider sees maxItems: 3 and no minimum, so a 1-2 item array is schema-valid, reaches execute, and is rejected with INVALID_SUGGESTED_QUESTIONS / retrySafe: false (:58-71). isEnabled (:91-96) then hides the tool for the rest of the turn. | A schema that can express both valid states and nothing else. | Dead-end failure mode - one malformed draft and the turn stores nothing, with no retry path. Already exercised at flight-agent-recovery-loop.test.ts:315-317. | Medium | DECISION NEEDED. A plain .min(3) is wrong: the empty array is how "no active search, clear stale suggestions" is expressed (:41-47). Option (a) keep 0..3 plus a clearOnly discriminator; option (b) PREFERRED .min(3).max(3) like trip-planner (context-tools.ts:116-123) and move clearing into the Step 1 finalize. Also consider per-string .max(80). | Step 2 | Open
G8 | B - Tool definition | No phase gate; "at most once" is the only constraint | "After it returns successfully, call no more tools", and never before core work. | isEnabled dedupes by requestId only (suggested-questions-tool.ts:91-96). It does not require core work to be complete and does not stop later tool calls. | A turn-phase gate. | The tool can fire mid-turn; nothing guarantees it is last. | Medium | Mirror the trip-planner gate (context-tools.ts:209-216: contextCaptured && !suggestionsUpdated && attempts < 2), adapted to "core work complete". | Step 2 | Open
G9 | C - State / context | A skipped call silently keeps last turn’s suggestions | The tool was mandatory and re-read searchKey at execution time, so every turn ended in a deliberate write. | prepareFlightAgentTurnContext clears only when there is no searchKey (flight-context.ts:345-347). On a read-only turn with an active search and no tool call, the previous turn’s three strings persist verbatim. | An end-of-turn finalize. The sibling has exactly this: finalizeTripPlannerTurn clears when !turnState.suggestionsUpdated (trip-planner/context/lifecycle.ts:422-425); trip-planner/runner.ts:434 clears on error. | Silent staleness, invisible to tests - the lenient live assertions check suggestions.length === 3 (flight-agent-intelligence-deep-chats-live.ts:789-801), which passes on stale data. | High | Add a flight turn-finalize plus a per-turn suggestionsUpdated flag. Correct regardless of the mandate decision, so do it first. | Step 1 | Open
G10 | C - State / context | Mutation tools wipe without refill | Same clearing, but the mandated end-of-turn write always refilled. | search-tool.ts:482 and filter/tool.ts:183 set suggestedQuestions = []; see the Evidence sheet for the count of turns that never refilled. | The guaranteed refill, not the clearing. | Empty suggestion chips after a search or filter - the most user-visible symptom. | High | Keep the clearing (it is correct invalidation) and close the hole via G1/G8/G9. | Step 1 | Open
G11 | D - Execution flow | Zero enforcement anywhere in the run | Prompt-level only there too, but the prompt said "mandatory". | toolChoice: ‘auto’ (config.ts:19-22); no output guardrail on the agent (agent.ts:234-240); no post-run inspection of toolCallLog in runner.ts:154-185; the max-turns recovery path deliberately excludes it from CORE_TOOLS (recovery-outcome.ts:6-10). | Any mechanism that notices the omission. | The prompt is the sole control, and it currently says "optional". | Medium | The G9 finalize is the enforcement point. Keep toolChoice: auto - forcing a specific tool would break the core tool loop. | Step 1 | Open
G12 | D - Verification | The test suite pins the gap open | n/a - this is local test debt. | NON_CORE_TOOLS strips the tool before scoring, rationale "must never decide a pass or fail" (flight-agent-conversation-cases.ts:26-27,53). flight-gap-contracts.test.ts:59 is named for the absence. In the report harness none of the 17 expectedTools arrays include it and validateTurn compares tool sequences by exact string equality (flight-agent-session-complex-report-live.ts:434-440). The one script that requires the call (flight-agent-suggested-questions-variation-live.ts:146-148) has no npm script and is never run. | Expectations that encode the mandate rather than its absence. | Restoring the mandate turns the report harness red on every turn before it turns anything green. | High | Flip the expectations as part of the change, not after it. | Step 4 | Open
G13 | D - Execution flow | No observability | n/a | .debug/flight-prompt-traces is metadata-only (captureMode "safe"; 61 files, 3 with modelCalls, 0 tool-call records). flight_agent.response (runner.ts:170-176) logs nothing about suggestions. | A per-turn record of whether the tool ran. | The call rate is unmeasurable in a running system; this gap was only visible by grepping recorded artifacts. | Medium | Log suggestionsUpdated and the suggestion count per turn. | Step 1 | Open
G14 | E - Docs | Docs still describe the mandate as live | n/a | flight-agent-recent-changes.md:251, flight-agent-context-flow.md:429, flight-agent-date-handling-multiturn.md:390 and prompts/prompt-with-error.md:232 all state it runs last on every turn. No doc calls it optional. | Agreement between the docs and the live prompt. | Anyone reading the docs concludes the rule is already enforced. | Low | Docs become correct once G1-G3 land; add the chain list and note that FLIGHT_PROD_PROMPT_TEXT is dead text. | Step 5 | Open

## Evidence
Evidence - re-tallied from artifacts/ on every run of this generator
Generated: 2026-10-01T09:36:30.585Z
Artifact files with recorded turns: 30
Method: per recorded turn, read the tool list (rawTools, else flightTools, else actualTools) and check whether it contains update_flight_suggested_questions. "Cleared not refilled" counts turns where flight_search or apply_filter ran - both wipe suggestedQuestions - and the tool was not called.
Call rate by core-tool signature - all recorded turns
Core tools in the turn | Turns | Tool called | Rate
flight_search | 52 | 51 | 98%
apply_filter | 50 | 25 | 50%
getGeneratedContractsContext | 46 | 1 | 2%
(no tool) | 28 | 0 | 0%
price_prediction_tool | 11 | 0 | 0%
apply_filter + flight_search | 8 | 7 | 88%
getGeneratedContractsContext + price_prediction_tool | 2 | 1 | 50%
flight_search + getGeneratedContractsContext | 2 | 0 | 0%
apply_filter + getGeneratedContractsContext | 1 | 1 | 100%
flight_search + price_prediction_tool | 1 | 0 | 0%
Call rate by core-tool signature - flight-conversation-* fixtures only (the set the fix verification re-runs)
Core tools in the turn | Turns | Tool called | Rate
apply_filter | 18 | 13 | 72%
flight_search | 16 | 16 | 100%
(no tool) | 12 | 0 | 0%
getGeneratedContractsContext | 11 | 0 | 0%
price_prediction_tool | 5 | 0 | 0%
apply_filter + getGeneratedContractsContext | 1 | 1 | 100%
apply_filter + flight_search | 1 | 1 | 100%
getGeneratedContractsContext + price_prediction_tool | 1 | 0 | 0%
Call rate by artifact group
Group | Turns | Tool called | Rate | Cleared not refilled
flight-conversation-* | 65 | 31 | 48% | 5
manager-flight-* | 93 | 40 | 43% | 15
manager-realistic-* | 43 | 15 | 35% | 10
TOTAL | 201 | 86 | 43% | 30
Target after the fix
Every core-tool signature row reaches 100%, including getGeneratedContractsContext, price_prediction_tool and (no tool) - the three that are effectively never called today - and "Cleared not refilled" reaches 0.

## Skip Scenarios
Scenario | Measured evidence | Why the current agent skips it
Informational question about current options | 0 of 11 turns called the tool | No chain covers getGeneratedContractsContext, and no mutation tool ran, so the "when called with an active search" wording never clearly applies.
Price / date intelligence | 0 of 5 turns | Same - prompt.ts:672-676 chains exist only in the dead reference text.
Clarification / missing-info turn with no tools | 0 of 12 turns | Production had an explicit standalone chain for exactly this case; the local prompt has none.
Filter-only turn | skipped on 5 of 18 turns | Called opportunistically, not reliably.
Under turn-budget pressure | licensed by prompt.ts:143 | The prompt tells the model to prioritise structured feedback over "optional work".
Manager mode | 43% and 35% call rates | The turn ends by emitting the structured output, and manager-output.ts:38 explicitly calls the work optional.
Non-deterministically, on identical input | search_filter_options turn 2 "Show nonstop flights only" - called in manager-flight-five-chats-live.json, not called in the byte-identical -traced-live.json | Nothing enforces it, so it is left to sampling.

## Fix Sequence
Step | Scope | Gaps | Why this order
Step 0 | This Excel register + extract the shared XLSX writer into scripts/lib/xlsx-workbook.ts | - | Track the gaps before changing behaviour.
Step 1 | Deterministic state correctness: suggestionsUpdated flag, flight turn finalize on success and error paths, per-turn logging | G9, G10, G11, G13 | Correct on its own merits and independent of the mandate decision. After this, a skipped call can no longer ship stale data.
Step 2 | Tool contract: required-terminal description, schema decision, isEnabled phase gate | G6, G7, G8 | The tool description must stop contradicting the mandate before the prompt asserts it.
Step 3 | Prompt authority: mandate wording, stop rule, chain list, checklist line, Manager-mode ordering | G1, G2, G3, G4, G5 | Raises the call rate once the state layer is already safe.
Step 4 | Tests: invert NON_CORE_TOOLS, rewrite flight-gap-contracts case, add the tool to the 17 expectedTools arrays, add the missing npm script | G12 | Must land with Step 3 - the report harness compares tool sequences by exact equality and would otherwise fail every turn.
Step 5 | Reconcile the four docs | G14 | Last, once behaviour is settled.

## Open Decisions
Topic | Detail | Owner / status
Who renders the suggestions? | context.flight.suggestedQuestions is persisted and emitted in the SSE done.flightContext payload (api/chat/orchestrator.ts:228), but public/ has zero references to "suggest" and the dashboard reads only showFlight and searchResults. The only reader today is the Flight agent’s own next-turn prompt (agent.ts:109-116), as anti-staleness input. Restoring the mandate buys production parity and correct state plus ~1 extra model call per turn, but no user-visible change until a renderer exists. | Open - confirm the real consumer (presumably the CheapOair mobile client).
G7 schema shape | Plain .min(3) breaks the empty-array clear path. Option (b) - exactly 3 at the schema level, clearing moved to the Step 1 finalize - is preferred. | Open - decide before Step 2.
Dead reference prompt | FLIGHT_PROD_PROMPT_TEXT (prompt.ts:148-995) carries all the mandatory language, is commented "Historical comparison reference only; never included in runtime instructions" (:147) and has zero references in src/, tests/ or scripts/. agent.ts:11 imports only FLIGHT_PROMPT. scripts/audit-session-prompts.ts:58 states the invariant: "FLIGHT_PROMPT is the single authoritative runtime prompt." | Resolved - do not edit that string; every rule must land in the live prompt.